## Phase 1
Phase 1(foundation):
TASK | TIME ESTIMATE
Define Flask server and folder structure
jobs_index.php
XML_RPC.php
serverFunctions.php
common_func.php
read_masterlog2.php
time_left.php
At the end of phase 1 - the jobs page works fine, with job running/paused state. And the REST api functions correctly
TOTAL TIME
Sequence of events
time_left.php | Completed
serverFunctions.php | Completed
common_func.php | Completed
XML_RPC.php | created REST_API.py in place of XML_RPC.php
read_masterlog2.php | Completed
jobs_index.php | Completed
Test the jobs_index page

## Phase 2
Phase 2(buildup):
TASK | TIME ESTIMATE
Setup WSGI and HTTPD configurations, add to puppet
Setup Virtual environment configuration and make it work together with pygash virtualenv
read_masterlog.php - Should be renamed so it's easier to distinguish from read_masterlog2
masterlog_list.php, masterlog_list2.php
masterlog.php, masterlog2.php
At the end of phase 2 - masterlog pages work, No need to manually configure bed to run the new_UI, puppet configuration is enough, Code is tight, few bugs, html pages have a template and hierarchy, new_UI errors are monitorable separately in a new file
TOTAL
Sequence of Events
Setup WSGI and HTTPD configurations on ansible + vagrant vm
Setup Virtual environment configuration and make it work together with pygash virtualenv
masterlog.php
read_masterlog.php - Should be renamed so it's easier to distinguish from read_masterlog2
masterlog_list.php
masterlog_list2.php
masterlog2.php
Note on B17: Can Praveen take it up? -Pulak Mehta
Note on B18: I'll do it -Pulak Mehta
Note on B19: I'll take it up -Pulak Mehta

## Phase 3
Phase 3(coverage):
TASK | TIME ESTIMATE
result.php
results_index.php
livesearch.php
Rewrite all .cgi files - as flask API calls
ip_list.php
login.php
server.php
All sites PHP files - Antwerp, Bratislava, Kanata, MtnView, Naperville, NuageAnt, NuageBa, NuageMv, NuageRa, genericSite.php
Status page - beds_status.php, index.php
comparepage.php
nav_bar.php
At the end of Phase 3 - The whole website works under the link /new_UI. No external dependency apart from static files, codebase has fewer bugs, and can be launched into beta testing mode(invite users to start using it)
TOTAL